## About
IPPF Risk Register
About
A risk register is a framework for identifying, assessing and recording the risks that your organisations faces. This example risk register has been produced exclusively for NCVO members. It can be used with our step-by-step risk management guide on NCVO Knowhow Nonprofit:
How-to manage risk
https://www.gov.uk/government/publications/charities-and-risk-management-cc26/charities-and-risk-management-cc26
IPPF Secretariat Risk Register 230919 |  | www.knowhownonprofit.org

## Regulatory and compliance risk
[11 empty] | This template is available exclusively to NCVO members at | www.knowhownonprofit.org
REGULATORY AND COMPLIANCE RISK | [10 empty] | The password to unprotect this worksheet and make changes to the layout and structure is | ncvo-risk-reg
Give each risk a code. This makes it easy to refer to it with others (eg in a meeting). | Identify your risks. | Analyse your risks by scoring the likelihood of them happening and the potential impact. |  |  | Think about your appetite for these risks. Give each one a target risk score that reflects the level of risk you’d be happy to accept. | List the controls that you currently have in place to reduce and control each risk. | Rescore the likelihood and potential impact of each risk with the controls in place. |  |  | If your residual risk score is higher than your target risk score (ie current controls don't reduce the risk to a level you're happy with), list the additional actions needed to reduce the risk further. | For ongoing assurance that risks are being controlled effectively, record who is responsible for each risk and when/how they should review it.
Risk code | Risk | Likelihood (1–5) | Impact (1–5) | Initial risk score | Target risk score | Current controls | Likelihood after controls (1–5) | Impact after controls (1–5) | Residual risk score | Actions required | Risk owner | Review (timeframe and process)
RC1 | Non complaince with GDPR or Fin Crime Policy | 4 | 4 | 16 | 8 | - Financial Crime Policy in place at IPPF. - Strong due dilligence process in place that are automated (Accuity). - Confidentiality and Information sharing policy in place. - All funding agreements include sections on compliance with financial crime policy. - Annual folllow with MAs on compliance wiht the FInancial Crime policy and more stringent procedures in place in cases of broadly sanctioned countries. | 4 | 3 | 12 | - Accuity system to be fully implemented in the Africa Regional Office - GDPR compliance audit to be completed. - Data Protection Policy to be reviewed and inorporated into the Policy Handbook. - DPO to check compliance against relevant data protection rules and regulations. - Training to be introduced across the Federation, covering data protection, anti criminal practices and financial crime. | Director Legal, Risk & Compliance. Director Finance & Technology (for Financial crime compliance, as interim charge) | - Once every quarter
RC2 | Cyber Security Attacks | 4 | 3 | 12 | 8 | - Cyber Essential certificaiton taken for IPPF and weaknessess addressed. - Current firewall protection controls in place. - Regular IT system penetration tests. - Regular training and awareness raising of phishing and cyber attacks. - O365 Backup solution ensuring adequate back up and retrieval processes of data on the cloud. | 4 | 2 | 8 | - Strengthen/ review and amend the Bring Your Own Device (BYOD) scheme currently in operation. - Improved Governance, Risk and Compliance (GRC) framework, user access management controls, administrators, email security through implementaiton of M365/ InTune/ Improved security protocols. - Upgrade IT policies and equipment management systems including setting up a strong BYOD policy | Director, Knowledge Information Systems Technologies | - Once every quarter
RC3 | Strained employment relations in the context o MeToo & BLM lead to rise in employment cases | 5 | 2 | 10 | 2 | -Strengthened project management through the restructuring and initiation of a signficant process with external support to look at race and its intersection with our work. - Woman's Leadership Programme launched. - Interim Director POC appointed while the purpose of the People, Organization and Culture division is reviewed. | 4 | 2 | 8 | - Recruitment of the Director, People, Organisation and Culture - Careful monitoring and management. Implementation of the programme in the context of S6. - Develop cohesive secretariat wide HR principles. - Implement additional mechanisms as recommended in the Anti-Racism programme of action | Director, People, Organization and Culture | - Once every quarter
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Note on F6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on G6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.
Note on N6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on O6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.

## Governance risk
[11 empty] | This template is available exclusively to NCVO members at | www.knowhownonprofit.org
GOVERNANCE RISK | [10 empty] | The password to unprotect this worksheet and make changes to the layout and structure is | ncvo-risk-reg
Give each risk a code. This makes it easy to refer to it with others (eg in a meeting). | Identify your risks. | Analyse your risks by scoring the likelihood of them happening and the potential impact. |  |  | Think about your appetite for these risks. Give each one a target risk score that reflects the level of risk you’d be happy to accept. | List the controls that you currently have in place to reduce and control each risk. | Rescore the likelihood and potential impact of each risk with the controls in place. |  |  | If your residual risk score is higher than your target risk score (ie current controls don't reduce the risk to a level you're happy with), list the additional actions needed to reduce the risk further. | For ongoing assurance that risks are being controlled effectively, record who is responsible for each risk and when/how they should review it.
Risk code | Risk | Likelihood (1–5) | Impact (1–5) | Initial risk score | Target risk score | Current controls | Likelihood after controls (1–5) | Impact after controls (1–5) | Residual risk score | Actions required | Risk owner | Review (timeframe and process)
G1 | Delay in onboarding of BoT and committees or prolonged transition that can affect clear understanding of roles, responsibilities, accountability mechanisms and effectively addressing conflicts of interest | 3 | 3 | 9 | 3 | - Boardable app in place ' Scheduled induction/on-board sessions. - Board retreats taking place. - Declarations of conflicts of interest forms in place. Effective staggering of board members. | 1 | 1 | 1 | -Organize scheduled orientation/induction for each Board committes upon appointment. - Implement on-going learning for Trustees and board committees members. - Regular reviews of board performance. | Director, Governance & Accreditation
G2 | Disconnect between the BOT and the grassroots movement leading to decision that do not necessarily address the needs of the members or meet their expectations | 3 | 5 | 15 | 6 | - Regular update meeting regarding board membership through virtual meetings and newsletters - Various platforms that enable regular engagement between the various board and committee members with membership organisations - Trustees participation in virtual Regional Forums - Roundtable and regular updates provided through the MA Forum microsite. - A rountdable on governance was organised in August and saw the participations' of all board committees members as part of the strategic plan development process. | 2 | 3 | 6 | - Board Chair and Board committees to host regular update meeting with the membership. - Chair to issue update letters to the members in a way that it speaks to volunteers directly and not just the MA's board members | Director, Governance & Accreditation
G3 | Failure to inspire the required governance reform at MA’s level | 3 | 5 | 15 | 6 | - MA governance reform strategy with clear ownership from the Board. - 20% of IPPF membership is embarked into the initiative with 37% applying for a slot. - Ongoing dialogue with the MA’s around governance, compliance, risk and assurance to encourage their participation in the reform process | 1 | 3 | 3 | - Implementation of the Global Assurance Mechanism. - Commencement of risk based internal audits on MAs. - Updated risk registers of MA's | Chairperson, IPPF/ Director, Governance & Accreditation
G4 | Failure of the NGC to attract and retain good caliber of governing bodies members | 2 | 5 | 10 | 5 | -Skill matrix in place. Use of external recruitment firm to attract required skills - Skills gap identified and communicated to NGC for recruitment efforts | 1 | 1 | 1 |  | Chair of NGC / Director, Governance & Accreditation
G5 | Failure to inspire, manage and lead a General Assembly that is inspirational, resilient, accountable and forward looking with a continued appetite for change. | 3 | 4 | 12 | 4 | - Regular update meeting with the membership - Governance roundtable organized and attended by all MAs - MA Forum microsite is being used and governance roundtable including consultation with selected MAs as part of the Board performance review process to keep the membership up to date -Regional forums attended by trustees as part of the on-going engagement with the membership | 2 | 2 | 4 | - Still to formalise regular virtual meetings with the specific participants of the GA on regular basis. i.e A maximum of twice a year | Chairperson, IPPF/ Director General
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Note on F6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on G6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.
Note on N6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on O6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.

## Financial risk
[13 empty] | This template is available exclusively to NCVO members at | www.knowhownonprofit.org
FINANCIAL RISK | [12 empty] | The password to unprotect this worksheet and make changes to the layout and structure is | ncvo-risk-reg
Give each risk a code. This makes it easy to refer to it with others (eg in a meeting). | Identify your risks. |  | Analyse your risks by scoring the likelihood of them happening and the potential impact. |  |  | Think about your appetite for these risks. Give each one a target risk score that reflects the level of risk you’d be happy to accept. |  | List the controls that you currently have in place to reduce and control each risk. | Rescore the likelihood and potential impact of each risk with the controls in place. |  |  | If your residual risk score is higher than your target risk score (ie current controls don't reduce the risk to a level you're happy with), list the additional actions needed to reduce the risk further. | For ongoing assurance that risks are being controlled effectively, record who is responsible for each risk and when/how they should review it.
Risk code | Risk |  | Likelihood (1–5) | Impact (1–5) | Initial risk score | Target risk score |  | Current controls | Likelihood after controls (1–5) | Impact after controls (1–5) | Residual risk score | Actions required | Risk owner | Review (timeframe and process)
F1 | Inability to comply with budgetary limits due to limited budgetary control and forecasting ability |  | 4 | 4 | 16 | 6 |  | - Management accounts are produced monthly and presented quarterly to C-FAR. - Budgetary control practices - Regular income and expenditure forecasts produced and reported to C-FAR. - Forex risk hedging system in place to prevent significant variances due to forex movement. -Month end/ year-end processes and practices in place -Regular reconciliation of MA grants (both commodities and cash) before release of the next instalment of core grant. | 2 | 3 | 6 | - Introduce income and expenditure forecasting effective 2021. - provide training to users to explain how accounting system tracks budgetaruy over-runs - Better planning and budgeting tool introduced - Increased recovery of staff costs from restricted projects is required in order for IPPF’s business model to be sustainable. Budget preparers still need to properly include salaries in direct costs for essential services (eg finance, safeguarding, assurance etc). Improved awareness to be achieved through training, policy etc. - Forex hedging strategy to be finalised and contracts to be entered and signed leading up to 2022. - guidance documents and training needs to be produced regarding month and year-end processes. - Expenditure and income forecasting to move from excel spreadsheets to NSPB (Netsuit). - Pyango (budgetary control tool) to be implemented as part of the NSPB implementation. | FInancial Controller/ Director, Finance & Technology with the support from all regional finance leads | - once every month - through monthly management accounts. - once every quarter by tracking progress of roll out of planning and budgeting tool.
F2 | Loss of funding from donors due to re-prioritization and also due to rise in fraud/ mismangement incidents across the Federation. |  | 4 | 4 | 16 | 6 |  | - Quick follow up on incident reports received through Safe Report, including regular updates to donors and charity commission (where required). - Robust anti criminal practices and financial crime policies in place. - Constant and proactive engagement with donors to ensure strong donor confidence. - Proactively scanning the donor environment for new opportunities and new donors that can support IPPF in delivery of its vision and mission. - Tracking all bidding opportunities and documenting reasons why bids are won or lost. | 3 | 3 | 9 | - IPPF Fraud Response Plan to be introduced. - Anti Criminal Practices Training to be rolled out across Federation - Ongoing work with Member Associations to build fund raising capacity and set up Social Enterprise Acceleration programme, to expedite income generation. | Director, Finance & Technology with support from all regional incident coordinators/ fraud leads | - once a month by tracking through the incident management report. - Once every three months - by tracking reports to the C-FAR and Bard
F3 | Disparate policies/ procedures implemented across the Secretarait, leading to inability of the management to compare numbers across offices |  | 4 | 3 | 12 | 8 |  | - Integrated enterprise resource planning system in place. - Regular follow up with all offices, to ensure practices are being followed. Making rectifications, where necessary in reports - Fortnightly meetings of the finance family (members from across the secretariat) being held to discuss issues and areas of concern | 2 | 4 | 8 | - Upgrade the Secretariat FInance Guide, including financial policies and accounting practices. Standard internal controls and processes to be mandated across the Secretariat. - Finalise the external audit policies and guidelines to improve the quality of external auditors work. - Regular follow up (including through the accreditation process) by RO teams to ensure similar mandates are prevailing at the MA level too. - Implement system improvement actions identified to ensure improved financial management. | FInancial Controller/ Director, Finance & Technology with the support from all regional finance and programme leads | - once every months - tracking progress made in implementation
F4 | IPPF's donors request return of funds due to non availablity of data from WHR MA's which are leaving IPPF. |  | 3 | 4 | 12 | 6 |  | - Deeds of variation signed by all WHR MA's - WHRO has agreed to share information with IPPF. -All key IPPF donors informed and kept updated. Transparency has been the key principle when engaging with donors. To date, no donor has expressed their intention to withdraw or freeze any funding to IPPF. | 2 | 3 | 6 | - Regular follow up with WHRO and MAs in the region, to try and ensure, this situaiton is prevented - Upgrade all funding agreements/ contracts, with partners/ Member Associations to ensure existence of a clear exit clause, if required. | Director Risk & Assurance | Bi Weekly
F5 | Negative impact on delivery of restricted projects as planned due to external factors (e.g. volatility of exchange rates, security risks in fragile countries) and internal factors (management capacity across the Federation) |  | 3 | 5 | 15 | 6 |  | - Project level risk mitigation plans (for large projects) in place. - Clear procurement strategy in place. - Strong controls set up through the contracting mechanism. - Regular financial and programmatic/ delivery monitoring. - Due diligence checks of all contractors/ vendors/ consultants/ partners. - Implementation of IPPF's fraud response guidelines and plans. - Regular audits (as per requirement) - Financial and programmatic delivery monitoring and review strengthened through Secretariat-wide monitoring process (QRM); production of quarterly restricted performance project update to DLT | 3 | 2 | 6 |  | Director, Programmes duly supported by the project team, Director, Finance & Technology and all programme and finance colleagues from regional offices | Once every quarter
[5 empty] | 0 | [5 empty] | 0
| Impact |  |  |  |  | Likelihood
| Descriptor | Score | Impact on service and reputation |  |  | Descriptor | Score | Example
| Insignificant | 1 | • no impact on service |  |  | Remote | 1 | may only occur in exceptional circumstances
|  |  | • no impact on reputation |  |  | Unlikely | 2 | expected to occur in a few circumstances
|  |  | • complaint unlikely |  |  | Possible | 3 | expected to occur in some circumstances
|  |  | • litigation risk remote |  |  | Probable | 4 | expected to occur in many circumstances
| Minor | 2 | • slight impact on service |  |  | Highly probable | 5 | expected to occur frequently and in most circumstances
• slight impact on reputation
• complaint possible
• litigation possible
| Moderate | 3 | • some service disruption
• potential for adverse publicity - avoidable with careful handling
• complaint probable
• litigation probable
| Major | 4 | • service disrupted
• adverse publicity not avoidable (local media)
• complaint probable
• litigation probable
| Extreme/Catastrophic | 5 | • service interrupted for significant time
• major adverse publicity not avoidable (national media)
• major litigation expected
• resignation of senior management and board
[5 empty] | 0 | [5 empty] | 0 | [5 empty] | • loss of beneficiary confidence
[5 empty] | 0 | [5 empty] | 0 |  |  |  | Likelihood
[5 empty] | 0 | [5 empty] | 0 |  |  |  | Descriptor | Score | Example
[5 empty] | 0 | [5 empty] | 0 |  |  |  | Remote | 1 | may only occur in exceptional circumstances
[5 empty] | 0 | [5 empty] | 0 |  |  |  | Unlikely | 2 | expected to occur in a few circumstances
[5 empty] | 0 | [5 empty] | 0 |  |  |  | Possible | 3 | expected to occur in some circumstances
[5 empty] | 0 | [5 empty] | 0 |  |  |  | Probable | 4 | expected to occur in many circumstances
[5 empty] | 0 | [5 empty] | 0 |  |  |  | Highly probable | 5 | expected to occur frequently and in most circumstances
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
[5 empty] | 0 | [5 empty] | 0
Note on F6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on G6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.
Note on N6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on O6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.

## Operational risk
[11 empty] | This template is available exclusively to NCVO members at | www.knowhownonprofit.org
OPERATIONAL RISK | [10 empty] | The password to unprotect this worksheet and make changes to the layout and structure is | ncvo-risk-reg
Give each risk a code. This makes it easy to refer to it with others (eg in a meeting). | Identify your risks. | Analyse your risks by scoring the likelihood of them happening and the potential impact. |  |  | Think about your appetite for these risks. Give each one a target risk score that reflects the level of risk you’d be happy to accept. | List the controls that you currently have in place to reduce and control each risk. | Rescore the likelihood and potential impact of each risk with the controls in place. |  |  | If your residual risk score is higher than your target risk score (ie current controls don't reduce the risk to a level you're happy with), list the additional actions needed to reduce the risk further. | For ongoing assurance that risks are being controlled effectively, record who is responsible for each risk and when/how they should review it.
Risk code | Risk | Likelihood (1–5) | Impact (1–5) | Initial risk score | Target risk score | Current controls | Likelihood after controls (1–5) | Impact after controls (1–5) | Residual risk score | Actions required | Risk owner | Review (timeframe and process)
O1 | Safeguarding, secruity and HR related | 4 | 3 | 12 | 6 | 1. Benefit survey and review recently undertaken 2. Safegurading point person in every region. 3. Incident management system in place, including management oversight of the Incident Management system through monthly, quarterly and annual reporting to DLT, C-FAR and the BoT 4. Organisational Security Advisor in place 5. Matrix management through Unified Secretariat 6. Mandatory safeguarding training in place 7. Security support provided to all offices by security advisor. | 3 | 3 | 9 | 1. HR function to be globalised throughout the Secretariat; 2. Training & compliance with law &regulationsecruity systems; 3.PDR system to be updated and rolled out. 4. Review of secrutiy function, policies, plans and procedrues and staff training, plan and develop cardre of regional point persons; 6. Review disaster recovery plan and improve as appropriate for all offices. | HR, Safeguarding and security point person in each RO; CO and Secruity Advisor with overall ownership of Director People, Organisation and Culture | Quarterly and Anually
O2 | Commodities and Stock outs | 4 | 3 | 12 | 4 | 1. MSI and IPPF’s Head of Procurement develop a joint action plan with UNFPA. 2. IPPF/ partners carries out commodity assessments so as to respond timely in instances of commodity shortages 3. Proposed solutions to specific weaknesses in the supply chain and assisting countries in securing necessary commodities 4. IPPF also in extreme circumstances can reach out to leading global manufacturers for production assurances. 5. Additional unrestricted funds received from Danida to support commodity security. | 3 | 3 | 9 | This risks realised in Q2 2021 due to significant cuts from FCDO to UNFPA, significantly impacting commodities to MAs. This risk mostly impacted MAs in Africa as they are particularly reliant on UNFPA supplies. 1. Internal audit recommendations of procurement to be implemented. 2.Working group to be fully established with supply team and ROs to support MAs in a) liaising with local government & UNFPA country offices for national quantification exercises; support local assessment of needs, and b) increase visibility of data from all partners in specific countries including UNFPA and implementing organizations like IPPF. | Programme Directors in all Region with final ownership of Director Programme in CO | Concurrent and regular
O3 | Lack of credibility | 3 | 3 | 9 | 2 | 1. Comprehensive SRHR programmes in place that gives upper hand over competitors - WISH programme received A* rating.. 2.Performance updates of restricted projects through the Quarterly Review Meeting (QRM) reports 3. Only aggregated unidentifiable information shared externally regarding clients records. 4. Engagement at various global, regional and national advcoacy forums 5. Global Lead Evidence and Impact and Director in place 6.Comprehensive data management strategy in place. 7. Strong external communications. | 2 | 3 | 6 | 1. To include QRM data of unrestricted programme (business plans) to ensure continued performance and relevance. 2. strengthen and standardise compliance checks with MAs and partners 3. Impact evaluation to be carried out. 4. Identify and invest in innovative and sustainable solutions. 5. Develop a strategy to better integrate and utilize restricted funding to support IPPF institutional priorities 6.Performs organisational and MA prorgamme data audit 7. Commence risk based internal audit to strengthen MAs. | All Regional Directors with overall responsibility of Director External Regionals, Director Finance and Technology and Director Programme at CO | Concurrent and regular
O4 | Lack of capacity and inflexible and outdated systems | 3 | 4 | 12 | 4 | 1. Netsuite application system reviewed 2. Matrix management within Unified Secretariat 3. Weekly DLT meetings where strategic issues are discussed | 3 | 3 | 9 | 1. Review policies and operationalise audit systems 2. Detailed review of all Secretrariat systems needs to be undertaken 3. Secretariat finance manual to be implemented. 4. Uniform, updated and timely induction arrangements for all new starters. 5. Timely and efficient working of Netsuite 6. Strong and uniform accountability system 7. Strong relationship with Staff Association 8. Planned review of detailed HR systems after the initial salary review | Director Finance and Admin at all RO levels and in CO Director People, Organisation and Culture and Director Finance and Technology | Annual CMIS audits, Regular systems reviews
O5 | Funding and sustainability | 1 | 1 | 1 | 1 | 1. Regular source of funding with strong donor relations 2. Donor meetings and engagment at various global advocacy forums 3. New partnerships and relationships developed 4. Investment in sustainability at MA levels | 1 | 1 | 1 | 1. Revamp website and maintain strong external communicaiton through all media channels - social and mass 2. Invest at regional levels to develop strong cadre of Business Development and Resource mobilisation 3. Adapt systems and processes to enhance local resource mobilition 4.Improve MA advocacy, communications and grant management | Regional Directors with main ownership from Director External Relations at CO | Regular
Note on F6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on G6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.
Note on N6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on O6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.

## External Risk
[11 empty] | This template is available exclusively to NCVO members at | www.knowhownonprofit.org
EXTERNAL RISK | [10 empty] | The password to unprotect this worksheet and make changes to the layout and structure is | ncvo-risk-reg
Give each risk a code. This makes it easy to refer to it with others (eg in a meeting). | Identify your risks. | Analyse your risks by scoring the likelihood of them happening and the potential impact. |  |  | Think about your appetite for these risks. Give each one a target risk score that reflects the level of risk you’d be happy to accept. | List the controls that you currently have in place to reduce and control each risk. | Rescore the likelihood and potential impact of each risk with the controls in place. |  |  | If your residual risk score is higher than your target risk score (ie current controls don't reduce the risk to a level you're happy with), list the additional actions needed to reduce the risk further. | For ongoing assurance that risks are being controlled effectively, record who is responsible for each risk and when/how they should review it.
Risk code | Risk | Likelihood (1–5) | Impact (1–5) | Initial risk score | Target risk score | Current controls | Likelihood after controls (1–5) | Impact after controls (1–5) | Residual risk score | Actions required | Risk owner | Review (timeframe and process)
E1 | Continuing political conservatism (re)creeping into SRHR investment, widening of mandate into less contentious areas - pandemic, migration/humanitarian, MNCH, FP | 4 | 5 | 20 | 6 | 1.Internal controls include sector leadership via: a) Donor advisory Group and other fora where more progressive/courageous donors + IPPF can co-create strategy for SRHR investment. b) Continued support via hosting, movement building and work with MA's who are able to counter conservative action locally, and strategic planning focused on capturing young and marginalised voices | 3 | 3 | 9 | 1. Capture younger voices from across the world and change the narrative, with support from progressive donors and with more strategic use of core funds. 2. Create a movement more powerful than a few bilateral donors, and break out of aid discourse that young people don't recognise. 3. Use #metoo; #aidtoo and #BLM as the launchpad to find that voice, and do a better job of linking this to all elements of IPPF's service offering including; brand and service design. 4.Continue to build virtual connections across existing and new platforms. Unlock resources and space for thought leadership in regions and countries less distracted by Coronavirus Disease-19, so that SRHR action can continue | Director External Relations | Quarterly
E2 | SRHR sector struggles to acclimatise to C-19, failing to adapt to new ways of working; ie virtual, need for mid/long range planning, and new power leadership. Critically, resources and infrastructure for thought leadership remains in Europe/US; yet Euro/US remains largely distracted by the pandemic | 4 | 5 | 20 | 10 | Almost all in person meetings have been moved on line, with non essential meetings cancelled. There are not yet adequate controls (beyond internal IPPF controls; i.e. DLT and hire of Head of Strategy and Planning) for better sharing thought leadership out of US/Europe, at least during the waves of the pandemic when distractions are at their greatest | 4 | 4 | 16 | Continue to build virtual connections; across existing and new platforms. Better plan for moments when travel will open up, and get better at moving quickly back into virtual as the pandemic unfolds. Unlock resources and space for thought leadership in regions and countries less distracted by C-19, so that SRHR action can continue. | Director External Relations | Quarterly
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Note on F6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on G6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.
Note on N6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on O6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.

## Strategic Risk
[11 empty] | This template is available exclusively to NCVO members at | www.knowhownonprofit.org
STRATEGIC RISK | [10 empty] | The password to unprotect this worksheet and make changes to the layout and structure is | ncvo-risk-reg
Give each risk a code. This makes it easy to refer to it with others (eg in a meeting). | Identify your risks. | Analyse your risks by scoring the likelihood of them happening and the potential impact. |  |  | Think about your appetite for these risks. Give each one a target risk score that reflects the level of risk you’d be happy to accept. | List the controls that you currently have in place to reduce and control each risk. | Rescore the likelihood and potential impact of each risk with the controls in place. |  |  | If your residual risk score is higher than your target risk score (ie current controls don't reduce the risk to a level you're happy with), list the additional actions needed to reduce the risk further. | For ongoing assurance that risks are being controlled effectively, record who is responsible for each risk and when/how they should review it.
Risk code | Risk | Likelihood (1–5) | Impact (1–5) | Initial risk score | Target risk score | Current controls | Likelihood after controls (1–5) | Impact after controls (1–5) | Residual risk score | Actions required | Risk owner | Review (timeframe and process)
S01 | Deteriorating CSO space and rising opposition undermine IPPFs ability to work | 4 | 3 | 12 | 8 | Monitor the situation. Engage with CSO alliances and highlight contribution of CSOs. Work with donor and local governments. | 3 | 3 | 9 |  | Director, External Relations with Director General | Quarterly
S02 | Inability to attract and retain volunteers | 3 | 4 | 12 | 6 | - The global reform is bedding down and national reform programme has gathered momentum. - Global and national governance reform to allow for internal and external Board members. | 2 | 3 | 6 | Successful leadership development programme implemented (Solution 6) | Director General with Diretor People, Organization and culture | Quarterly
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Note on F6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on G6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.
Note on N6: 1 = Rare. Not likely to happen or will only happen in exceptional circumstances. 2 = Unlikely. Not expected to happen, but there is a remote possibility that it will occur. 3 = Possible. May occur on some occasions but not frequently. 4 = Likely. Is likely to occur or will happen on more occasions than not. 5 = Certain. Likely to occur in the majority of cases.
Note on O6: 1 = Insignificant. One or moreof the following: no impact on service, no impact on reputation, complaint unlikely, risk of litigation remote. 2 = Minor. One or moreof the following: slight impact on service, slight impact on reputation, complaint possible, litigation possible. 3 = Moderate. One or moreof the following: some service disruption, potential for adverse publicity (avoidable with careful handling), complaint probable, litigation probable. 4 = Significant. One or moreof the following: service disrupted, adverse publicity unavoidable (local media), complaint probable, litigation probable. 5 = Major. One or moreof the following: service interrupted for significant time, major adverse publicity not avoidable (national media), major litigation expected, resignation of senior management and board, widespread loss of beneficiary confidence.